## ManageEngine Report Framework
VNG Corporation
Requests
Generated by Tính. Hồ Tính on : Jun 15, 2026 04:24 PM
Total records : 7
Request ID | Subject | Requester | Technician | Urgency | Created Date | DueBy Date | Status | Site | Priority | Group | Is Service Request | Created By | Completed Date | Assigned Time | Approval Status | Last Update Time | Impact | Testing Document | Test by | Test date | ITSM Approved by | ITSM Approved Date | Scheduled Start Time | Scheduled End Time | Resolved Date | Actual Time Start | Actual Time End
56238 | FW: VNG- T11.25 Lỗi in sổ phụ vẫn hiện thị tên cũ Công Ty Cổ phần VNG | Thảo. Nguyễn Thụy Phương | Tính. Hồ Tính | Low | 2026-04-02 17:16 | 2026-04-09 17:16 | Closed | VNG Campus | Low | ERP Helpdesk | false | System | 2026-04-12 17:16 | 2026-04-11 17:16 | - | 2026-04-12 17:16 | Low | - | - | - | hainh5 | - | - | - | 2026-04-12 05:16 | 2026-04-12 17:16 | 2026-04-14 17:16
56343 | [SOX ITGC] Tạo bảng Access Matrix mapping từ hệ thống theo nghiệp vụ | Tính. Hồ Tính | Tính. Hồ Tính | Low | 2026-06-02 17:16 | 2026-06-09 17:16 | Closed | VNG Campus | Low | ERP Helpdesk | false | Tính. Hồ Tính | 2026-06-12 17:16 | 2026-06-11 17:16 | - | 2026-06-12 17:16 | Low | - | - | - | hainh5 | - | - | - | 2026-06-12 05:16 | 2026-06-12 17:16 | 2026-06-14 17:16
56344 | [SOX ITGC] Gửi Review Access định kỳ theo policy | Tính. Hồ Tính | Tính. Hồ Tính | Low | 2026-01-02 17:16 | 2026-01-09 17:16 | Closed | VNG Campus | Low | ERP Helpdesk | false | Tính. Hồ Tính | 2026-01-12 17:16 | 2026-01-11 17:16 | - | 2026-01-12 17:16 | Low | - | - | - | hainh5 | - | - | - | 2026-01-12 05:16 | 2026-01-12 17:16 | 2026-01-14 17:16
56345 | [SOX ITGC] Cập nhật tài liệu MA - MC - MO | Tính. Hồ Tính | Tính. Hồ Tính | Low | 2026-01-02 17:16 | 2026-01-09 17:16 | Cancelled | VNG Campus | Low | ERP Helpdesk | false | Tính. Hồ Tính | 2026-01-12 17:16 | 2026-01-11 17:16 | - | 2026-01-12 17:16 | Low | - | - | - | hainh5 | - | - | - | 2026-01-12 05:16 | 2026-01-12 17:16 | 2026-01-14 17:16
56570 | TEST | An. Nguyễn Thị Trường (7) | Tính. Hồ Tính | Low | 2026-04-02 17:16 | 2026-04-09 17:16 | Closed | VNG Campus | Low | ERP Helpdesk | false | Tuân. Nguyễn Đình (2) | 2026-04-12 17:16 | 2026-04-11 17:16 | - | 2026-04-12 17:16 | Low | - | - | - | - | - | - | - | 2026-04-12 05:16 | 2026-04-12 17:16 | 2026-04-14 17:16
56645 | DC251226017 - Lỗi import phiếu, xóa phiếu | Giang. Bùi Thị Hà (3) | Tính. Hồ Tính | Urgent | 2026-06-02 17:16 | 2026-06-09 17:16 | Closed | VNG Campus | High | ERP Helpdesk | false | System | 2026-06-12 17:16 | 2026-06-11 17:16 | Approved | 2026-06-12 17:16 | Low | - | - | - | hainh5 | - | - | - | 2026-06-12 05:16 | 2026-06-12 17:16 | 2026-06-14 17:16
56664 | Trả lời: Check BUR | Trí. Đỗ Minh (4) | Tính. Hồ Tính | Low | 2026-06-02 17:16 | 2026-06-09 17:16 | Closed | VNG Campus | Low | ERP Helpdesk | false | System | 2026-06-12 17:16 | 2026-06-11 17:16 | - | 2026-06-12 17:16 | Low | - | - | - | hainh5 | - | - | - | 2026-06-12 05:16 | 2026-06-12 17:16 | 2026-06-14 17:16
Formulas:
DueBy Date = [Created Date]+7
Completed Date = [DueBy Date]+3
Assigned Time = [Completed Date]-1
Last Update Time = [Completed Date]
Resolved Date = [Last Update Time]-0.5
Actual Time Start = [Resolved Date]+0.5
Actual Time End = [Actual Time Start]+2